## Overall
ABT Design & Implementation Status
Smoke Test TC | # Check Point | ABT Design Status | Implement Status
MTC-MSC-0010 Create a route | 17 | 100% | 100%
MTC-SHP-0010 Create New Shipments | 14 | 100% | 100%
MTC-SHP-0020 Assign Shipments to Driver | 9 | 100% | 100%
MTC-CLC-0230 Dispatch Shipment in CellComm web page | 25 | 100% | 100%
MTC-FNC-0010 Set Shipment Complete | 16 | 100% | 100%
MTC-FNC-0090 Add Special Service with Shipment in Finish status | 15 | 100% | 100%
Total | 96 | 100% | 100%
ABT Design & Implementation Trend
| 1/19/2015 | 1/20/2016 | 1/21/2017 | 1/22/2018 | 1/23/2019 | 1/26/2020 | 1/27/2021 | 1/28/2022 | 1/29/2023 | 1/30/2024 | 2/4/2025 | 2/5/2026
total % design | 65% | 76% | 76% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
total % implement | 21% | 38% | 59% | 69% | 73% | 82% | 87% | 89% | 93% | 97% | 98% | 100%

## Smoke Test
# | Client Test Case | TC Status | Client VP | Corresponding TM | Corresponding TC | TA Path | ABT Design Status | Automation Status | Note | Manual Owner | Design Date | Auto Owner | Auto Date | Reviewed By | Last Review Date | Review Status | Format Review | Scripting Review
1 | MTC-MSC-0010 Create a route | Completed | Step 1: Master Schedules main page is displayed. | Authenticate Master Schedules | TC_002: Login with correct credentials >> TO_002 | /Tests/Master Schedules/Business Object/Management/Home Page/Interaction/Value Entry Form/Authenticate Master Schedules | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19 | Son Ly | 2015-01-19 | Completed
|  |  | Step 2: The selected customer's main page is displayed. | Master Schedules Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_001 | /Tests/Master Schedules/Business Object//Management/Home Page/Interaction/UI/Master Schedules Home Page-UI Control Validation | Completed | Completed |  |  |  | Son Ly | 2015-01-20 | Son Ly | 2015-01-20 | Completed
|  |  | Step 3: Two diferents options are displayed and available (Shipment Details, Orders). | Master Schedules Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_002 | /Tests/Master Schedules/Business Object//Management/Home Page/Interaction/UI/Master Schedules Home Page-UI Control Validation | Completed | Completed |  |  |  | Son Ly | 2015-01-20 | Son Ly | 2015-01-20 | Completed
|  |  | Step 4: The information is typed in the application | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_001 | /Tests/Master Schedules/Business Object//Management/Home Page/Interaction/UI/Master Schedules Home Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 5: The next columns are displayed: Edit link, Sequence, Type, Site Code, Site Name,Action, Transit Days, Iterations, Req Match Days, Delete "x" and Add "+" icon. | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_002 | /Tests/Master Schedules/Business Object//Management/Home Page/Interaction/UI/Master Schedules Home Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 6: A pop up window is displayed. | New Route Page-UI Links | TC_001: Links in New Route page work >> TO_001 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Links | Completed | Completed |  |  |  | Huong Huynh | 2015-01-19
|  |  | Step 7: All data is displayed. | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_001 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 8: Validation completed | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_001 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 9: The entered data is saved and the Stops tab display is available. | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_001, TO_003 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 10: A new stop is displayed in a new Row. | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_002 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 11: Stop's fields are displayed. | New Route Page-UI Links | TC_001: Links in New Route page work >> TO_001 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Links | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 12: The new data of the added stop is saved. | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_001,TO_003 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 13: Validation completed | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_001 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 14: The new order is displayed in the grid. | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_004 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 15: Confirmation message is displayed | New Route Page-UI Control Validation | TC_001: Controls in New Route work >> TO_005 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/New Route Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 16: Confirmation message is closed and another message is displayed: "Route <RouteName> has been created" | Create, Update, Copy, Deactivate and Delete Route | TC_001: Creating Route works >> TO_001 | /Tests/Master Schedules/Business Object/Route/LifeCycle/Create, Update, Copy, Deactivate and Delete Route | Completed | Completed |  |  |  | Huong Huynh | 2015-01-20
|  |  | Step 17: User is logged off the application. | Authenticate Master Schedules | TC_003: Logout Fleet Manager >> TO_003 | /Tests/Master Schedules/Business Object/Management/Home Page/Interaction/Value Entry Form/Authenticate Master Schedules | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19
2 | MTC-SHP-0010 Create New Shipments | Completed | Step 1: Master Schedules main page is displayed | Authenticate Master Schedules | TC_002: Login with correct credentials >> TO_002 | /Tests/Master Schedules/Business Object/Management/Home Page/Interaction/Value Entry Form/Authenticate Master Schedules | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19
|  |  | Step 2: The selected customer's menu options are displayed | Master Schedules Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_001 | /Tests/Master Schedules/Business Object//Management/Home Page/Interaction/UI/Master Schedules Home Page-UI Control Validation | Completed | Completed |  |  |  | Son Ly | 2015-01-20 | Son Ly | 2015-01-20 | Completed
|  |  | Step 3: Related routes are displayed in the result's grid | Master Schedules Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_002 | /Tests/Master Schedules/Business Object//Management/Home Page/Interaction/UI/Master Schedules Home Page-UI Control Validation | Completed | Completed |  |  |  | Son Ly | 2015-01-20 | Son Ly | 2015-01-20 | Completed
|  |  | Step 4: The route is displayed in the grid | BatchUpdate Page-UI Links | TC_001: Links work >> TO_001 | /Tests/Master Schedules/Business Object/Route/Interaction/UI/BatchUpdate Page-UI Links | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-21
|  |  | Step 5: A confirmation message is displayed. (e.g., SO has been started). The Update & RunSO button is disabled | Create And Cancel Buy Shipment | TC_001: Create Buy Shipment By Run SO >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/LifeCycle/Create And Cancel Buy Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-19
|  |  | Step 6: The status is displayed as SUCCESS, the Update & RunSO button is available | Create And Cancel Buy Shipment | TC_001: Create Buy Shipment By Run SO >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/LifeCycle/Create And Cancel Buy Shipment | Completed | Completed
|  |  | Step 7: MCP main page is displayed | Authenticate MCP Report | TC_001: Login with correct credentials >> TO_001 | /Tests/MCP Report/Management/Home Page/Interaction/Value Entry Form/Authenticate MCP Report | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19 | Son Ly | 2015-01-19 | Completed
|  |  | Step 8: Main page is displayed | MCP Report Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_001 | /Tests/MCP Report/Management/Home Page/Interaction/UI/MCP Report Home Page-UI Control Validation | Completed | Completed |  |  |  | Son Ly | 2015-01-20 | Son Ly | 2015-01-20 | Completed
|  |  | Step 9: The status is displayed as Success and the shipment number is displayed in the Message text column. (e.g., OTM Order [20130828-482700-SFTK_TEST_8/27-001] created. [11882];Shipment [20130828-482700-SFTK_TEST_8/27] created (11883)) | Create And Cancel Buy Shipment | TC_001: Create Buy Shipment By Run SO >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/LifeCycle/Create And Cancel Buy Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-19
|  |  | Step 10: MCP window is closed | MCP Report Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_002 | /Tests/MCP Report/Management/Home Page/Interaction/UI/MCP Report Home Page-UI Control Validation | Completed | Completed |  |  |  | Son Ly | 2015-01-20 | Son Ly | 2015-01-20 | Completed
|  |  | Step 11: OTM main page is displayed | Authenticate Fleet Manager | TC_002: Login with correct credentials >> TO_002 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/Value Entry Form/Authenticate Fleet Manager | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19
|  |  | Step 12: Buy Shipment Finder page is displayed | Fleet Manager Home Page-UI Links | TC_001: Left menu links work >> TO_001 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/UI/Fleet Manager Home Page-UI Links | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 13: Shipment's results table is displayed with the information | Buy Shipment Finder Page-Search Shipment | TC_001: Searching Shipment from Buy Shipment with valid data in Shipment tab >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Functional/Buy Shipment Finder Page-Search Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-19
|  |  | Step 14: OTM application is closed | Authenticate Fleet Manager | TC_003: Logout Fleet Manager >> TO_003 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/Value Entry Form/Authenticate Fleet Manager | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19 | Son Ly | 2015-01-19 | Completed
3 | MTC-SHP-0020 Assign Shipments to Driver | Completed | Step 1: Fleet Manager displayed home page | Authenticate Fleet Manager | TC_002: Login with correct credentials >> TO_002 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/Value Entry Form/Authenticate Fleet Manager | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19
|  |  | Step 2: Buy Shipment Finder page is displayed. | Fleet Manager Home Page-UI Links | TC_001: Left menu links work >> TO_001 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/UI/Fleet Manager Home Page-UI Links | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 3: Shipment is displayed in the result's grid. | Buy Shipment Finder Page-Search Shipment | TC_001: Searching Shipment from Buy Shipment with valid data in Shipment tab >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Functional/Buy Shipment Finder Page-Search Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-19
|  |  | Step 4: Shipmen details are displayed. | Buy Shipment Result Page-UI Links | TC_001: Links in Buy Shipment Result page work >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Interaction/UI/Buy Shipment Result Page-UI Links | Completed | Completed |  |  |  | Thao Ton | 2015-01-20
|  |  | Step 5: Assign Driver to Shipment - Override Criteria pop up window is displayed. | Buy Shipment Actions Page-UI Links | TC_001: Links in Buy Shipment Actions page work >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Interaction/UI/Buy Shipment Actions Page-UI Links | Completed | Completed |  |  |  | Thao Ton | 2015-01-20
|  |  | Step 6: Assign Driver to Shipment page with the Selected and Affected Shipments grids is displayed. | Assign, Force Assign And Unassign Driver to Shipment | TC_001: Assign driver to shipment >> TO_001 | /Tests/Fleet Manager/Business Transaction/Assign, Force Assign And Unassign Driver to Shipment | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 7: Buy Shipment details page is displayed | Fleet Manager Home Page-UI Links | TC_001: Left menu links work >> TO_001 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/UI/Fleet Manager Home Page-UI Links | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 8: The Driver ID is displayed in the field. | Assign, Force Assign And Unassign Driver to Shipment | TC_001: Assign driver to shipment >> TO_001 | /Tests/Fleet Manager/Business Transaction/Assign, Force Assign And Unassign Driver to Shipment | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 9: User is logged off from the application. | Authenticate Fleet Manager | TC_003: Logout Fleet Manager >> TO_003 | /Tests/Fleet Manager/Management and Information/Home Page/Functional/Authenticate Fleet Manager | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19
4 | MTC-CLC-0230 Dispatch Shipment in CellComm web page | Completed | Pre-condition: 1. The driver has shipment assigned 2. There is an Equipment in "EQ_AVAILABLE – EMPTY status" and belongs to assigned Equipment Type ID 3. There is a Power Uit in PU_AVAILABLE status |  |  |  | Completed | Completed |  |  |  | Huony Huynh | 2015-01-26
|  |  | Step1: Login to Cellcomm web application with valid credentials. http://qawebapps.logistics.penske.com/penske/CellComm4/ManageResources Expected Result: Manage Resources tab is displayed in the main page. | Authenticate CellComm | TC_002: Login with correct credentials >> TO_002 | /Tests/CellComm/Management and Information/Home Page/Interaction/Value Entry Form/Authenticate CellComm | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step2: Click on Dispatch tab Expected Result: Dispatch page is displayed. Some fields should be displayed: Shipment ID Date Shipment | CellComm Home Page-UI Control Validation Dispatch Page-UI Elements | TC_001: All tabs in Home page works >> TO_001 TC_001: UI Elements of Dispatch Page are displayed >> TO_001 | /Tests/CellComm/Management and Information/Home Page/Interaction/UI/CellComm Home Page-UI Control Validation /Tests/CellComm/Shipment/Interaction/UI/Dispatch Page-UI Elements | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step3: Click on Get Shipment button Expected Result: Error message is displayed beside Route name field (e.g., Error: Enter Valid Search Criteria). The field is displayed in red color. | Depart From Validation Dispatch Page-UI Control Validation | TC_001: Error message displays when submitting form with missing data >> TO_001 TC_001: Error message displays in correct colour >> TO_001 | /Tests/CellComm/Shipment/Interaction/Value Entry Form/Depart From Validation /Tests/CellComm/Shipment/Interaction/UI/Dispatch Page-UI Control Validation | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step 4: Delete the information on Date field Expected Result: An error message is displayed "Error: Invalid Date" | Depart From Validation | TC_002: Error message displays when input invalid data >> TO_002 | /Tests/CellComm/Shipment/Interaction/Value Entry Form/Depart From Validation | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step 5: Select a valid date Expected Result: The shipmend field is refreshed with the valid routes that has driver assigned | Dispatch Page-UI Control Validation | TC_002: Combo box works >> TO_002 | /Tests/CellComm/Shipment/Interaction/UI/Dispatch Page-UI Control Validation | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step 6: Select "blank" option in Shipment field and click on Get shipment button Expected Result: An error message is displayed "Error: Enter Valid Search Criteria" | Depart From Validation | TC_002: Error message displays when input invalid data >> TO_003 | /Tests/CellComm/Shipment/Interaction/Value Entry Form/Depart From Validation | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step 7: Select a valid route and click on Get shipment button Expected Result: Result's grid is displayed with the related shipment found | Dispatch Page-Search Shipment | TC_001: Searching shipment by Date and Route >> TO_001 | /Tests/CellComm/Shipment/Functional/Dispatch Page-Search Shipment | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step 8: Search a valid shipment with case sensitive (e.g 20141028-425400-999sfttkvk) Expected Result: The grid is populated with the related messages | Dispatch Page-Search Shipment | TC_002: Searching shipment by Shipment name >> TO_002 | /Tests/CellComm/Shipment/Functional/Dispatch Page-Search Shipment | Completed | Completed
|  |  | Step 9: Fill out all the fields with valid data: Shipment ID: (e.g., Shipment planned departure date with driver assigned). Click on Get Shipment button. Expected Result: Results table is displayed with all stops related with the found shipments. In the first stop the link 'Arrive" should be displayed in the action column. | Dispatch Page-Search Shipment Dispatch Page-UI Elements | TC_003: Searching shipment by all data >> TO_003 TC_002: UI Elements of Search grid display | /Tests/CellComm/Shipment/Functional/Dispatch Page-Search Shipment /Tests/CellComm/Shipment/Interaction/UI/Dispatch Page-UI Elements | Completed | Completed |  |  |  | Giang Nguyen
|  |  | Step 10: Click on Arrive link in the first stop Expected Result: Arrival Form is displayed. | Dispatch Page-UI Links | TC_001: Arrive and Depart links work >> TO_001 | /Tests/CellComm/Shipment/Interaction/UI/Dispatch Page-UI Links | Completed | Completed
|  |  | Step 11: Fill out the mandatory fields. Trailer: (e.g., ######). Tractor: Displays the data typed in CCFM. Arrival Date/Time: Displays the data created in Master Schedules. Click on Submmit button. Expected Result: Arrival Form is closed, the typed Arrival Date/Time is displayed in the column and the Depart link should be displayed. Note: The Timezone should be the same that shipment Arrival date should be greater than estimated | Dispatch Page-Dispatch a Shipment | TC_001: Arriving a stop >> TO_001 | /Tests/CellComm/Shipment/Functional/Dispatch Page-Dispatch a Shipment | Completed | Completed |  |  |  | Huony Huynh | 2015-01-26
|  |  | Step 12: Click on Depart link from the first shipment's stop. Expected Result: Departure Form is displayed. | Dispatch Page-UI Links | TC_001: Arrive and Depart links work >> TO_002 | /Tests/CellComm/Shipment/Interaction/UI/Dispatch Page-UI Links | Completed | Completed
|  |  | Step 13: Fill out the mandatory fields. Hub Miles: (e.g., 10). Fuel Level: (e.g., 8). Trailer: (e.g., ######). Tractor: (e.g., ######). Departure: (e.g., Same as scheduled). BOL: (e.g., optional). Weight: (e.g., optional). Pieces: (e.g., optional). Late arrival Code: (e.g., optional). Late Departure Code: (e.g., optional). Meal brak time: (e.g., optional). Delivery Exception: (e.g., optional). Spotting: (e.g., optional). Drop Hook: (e.g., optional). Click on Submit Query button. Expected Result: Departure window is closed. The Departure Date/Time is displayed in the column of the stop. Arrive link is displayed in the follow stop on the Action column. | Dispatch Page-Dispatch a Shipment | TC_002: Departing a stop >> TO_002 | /Tests/CellComm/Shipment/Functional/Dispatch Page-Dispatch a Shipment | Completed | Completed |  |  |  | Huony Huynh | 2015-01-26
|  |  | Step 14: Validate the "Fuel Stop", "Meal Break", "Layover", "Rest Break" and "Break Down" buttons are displayed Expected Result: The buttons is displayed correctly | Dispatch Page-Dispatch a Shipment | TC_002: Departing a stop >> TO_003 | /Tests/CellComm/Shipment/Functional/Dispatch Page-Dispatch a Shipment | Completed | Completed
|  |  | Step 15: Click on Meal Break button Expected Result: A meal break pop up window is displayed | Dispatch Page-UI Control Validation | TC_003: Button works >> TO_003 | /Tests/CellComm/Shipment/Interaction/UI/Dispatch Page-UI Control Validation | Completed | Completed
|  |  | Step 16: Fill out the following fields: Hub Miles: (e.g., 100) Arrival Date/Time (e.g., Actual date + 12:00:00) Departure Date/Time (e.g. Actual date + 12:30:00) Time Zone: (e.g., EST5EDT) Street: (e.g: 3000 Auburn Dr) City: (e.g., Beachwood) State: (e.g., OH) Expected Result: All information is displayed | Meal Break Page-UI Control Validation | TC_001: Proper data displays after input >> TO_001 | /Tests/CellComm/Shipment/Interaction/UI/Meal Break Page-UI Control Validation | Completed | Completed
|  |  | Step 17: Click on Submit Query button Expected Result: Pop up window is closed. New NFR stop is added | Meal Break Page-Submit Meal Break | TC_001: Submit meal break >> TO_001 | /Tests/CellComm/Shipment/Functional/Meal Break Page-Submit Meal Break | Completed | Completed
|  |  | Step 18: Please complete all stops. Expected Result: All stops are completed. | Dispatch Page-Dispatch a Shipment | TC_003: Arrive and Depart other stops >> TO_004 | /Tests/CellComm/Shipment/Functional/Dispatch Page-Dispatch a Shipment | Completed | Completed
|  |  | Step 19: Go Back to CCFM, click on the Buy Shipments option in the left menu Expected Result: Shipments Search page is displayed. | Fleet Manager Home Page-UI Links | TC_001: Left menu links work >> TO_001 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/UI/Fleet Manager Home Page-UI Links | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 20: In the Shipment ID field, type the finished shipment in Cellcomm (e.g., 20130822-482700-SFTK), from the dropdown list select Begins with and then click on Search button. Expected Result: Reult's grid is displayed with the related shitments found. | Buy Shipment Finder Page-Search Shipment | TC_001: Searching Shipment from Buy Shipment with valid data in Shipment tab >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Functional/Buy Shipment Finder Page-Search Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-19
|  |  | Step 21: Click on the shipment. Expected Result: Details' page is displayed. | Buy Shipment Result Page-UI Links | TC_001: Links in Buy Shipment Result page work >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Interaction/UI/Buy Shipment Result Page-UI Links | Completed | Completed |  |  |  | Thao Ton | 2015-01-20
|  |  | Step 22: Click on Status button. Expected Result: Statuses window is displayed. | Buy Shipment Page-UI Control Validation | TC_001: Buttons in Buy Shipment page work >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Interaction/UI/Buy Shipment Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 23: Verify the status of the shipment, SHIP_FINISHED status should be Yes. Expected Result: In the status value column, the shipment status is displayed correctly (e.g., SHIP_FINISHED_YES). | Dispatch Page-Dispatch a Shipment | TC_004: Shipment status after dispatched >> TO_005 | /Tests/CellComm/Shipment/Functional/Dispatch Page-Dispatch a Shipment | Completed | Completed
|  |  | Step 24: Log off from the applications. Expected Result: CCFM and Cellcomm applications are logged off. | Authenticate Fleet Manager Authenticate CellComm | TC_003: Logout Fleet Manager >> TO_003 TC_003: Logout CellComm >> TO_003 | /Tests/Fleet Manager/Management and Information/Home Page/Functional/Authenticate Fleet Manager /Tests/CellComm/Management and Information/Home Page/Interaction/Value Entry Form/Authenticate CellComm | Completed | Completed
5 | MTC-FNC-0010 Set Shipment Complete | Completed | Step 1: Financials page is displayed | Authenticate Financials | TC_002: Login with correct credentials >> TO_002 | /Tests/Financials/Home Page/Interaction/Value Entry Form/Authenticate Financials | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 2: Customer is selected | Financials Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_001 | /Tests/Financials/Home Page/Interaction/Interaction/UI/Financials Home Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 3: Shipments page is displayed | Financials Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_002 | /Tests/Financials/Home Page/Interaction/Interaction/UI/Financials Home Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 4: Information is displayed | Search Shipments To Complete Page-UI Control Validation | TC_001: Controls of Search Shipments To Complete page work >> TO_001 | /Tests/Financials/Shipment Modifications/Interaction/UI/Search Shipments To Complete Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 5: Result is displayed correctly | Search Shipments To Complete Page-Search Shipment | TC_001: Search criteria with shipment id >> TO_001 | /Tests/Financials/Shipment Modifications/Functional/Search Shipments To Complete Page-Search Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 6: Shipments is marked correctly | Search Shipments To Complete Page-UI Control Validation | TC_001: Controls of Search Shipments To Complete page work >> TO_003 | /Tests/Financials/Shipment Modifications/Interaction/UI/Search Shipments To Complete Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 7: Message 'Changes Submitted' is displayed correctly | Search Shipments To Complete Page-Set Shipment Complete | TC_001: Search shipment with all values >> TO_001 | /Tests/Financials/Shipment Modifications/Functional/Search Shipments To Complete Page-Set Shipment Complete | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-21
|  |  | Step 8: CCFM main page is displayed. | Authenticate Fleet Manager | TC_002: Login with correct credentials >> TO_002 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/Value Entry Form/Authenticate Fleet Manager | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 9: Buy Shipments page is displayed. | Fleet Manager Home Page-UI Links | TC_001: Left menu links work >> TO_001 | /Tests/Fleet Manager/Management and Information/Home Page/Interaction/UI/Fleet Manager Home Page-UI Links | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-20
|  |  | Step 10: The shipment is displayed in the grid results. | Buy Shipment Finder Page-Search Shipment | TC_001: Searching Shipment from Buy Shipment with valid data in Shipment tab >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Functional/Buy Shipment Finder Page-Search Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-19
|  |  | Step 11: Shipment's details are displayed. | Buy Shipment Result Page-UI Links | TC_001: Links in Buy Shipment Result page work >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Interaction/UI/Buy Shipment Result Page-UI Links | Completed | Completed |  |  |  | Thao Ton | 2015-01-20
|  |  | Step 12: Statuses pop up window is displayed. | Buy Shipment Page-UI Control Validation | TC_001: Buttons in Buy Shipment page work >> TO_001 | /Tests/Fleet Manager/Business Objects/Shipment/Interaction/UI/Buy Shipment Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 13: The shipment status for the SHIP_COMPLETE Type should be SHIP_COMPLETE_YES. | Search Shipments To Complete Page-Set Shipment Complete | TC_001: Search shipment with all values >> TO_002 | /Tests/Financials/Shipment Modifications/Functional/Search Shipments To Complete Page-Set Shipment Complete | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-21
|  |  | Step 14: Search Buy Shipment Special Service page is displayed. | Financials Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_003 | /Tests/Financials/Home Page/Interaction/Interaction/UI/Financials Home Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 15: The complleted shipment should be displayed. | Search Shipments To Complete Page-Set Shipment Complete | TC_001: Search shipment with all values >> TO_003 | /Tests/Financials/Shipment Modifications/Functional/Search Shipments To Complete Page-Set Shipment Complete | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-21
|  |  | Step 16: The user is logged off from the Financials and CCFM applications. | Authenticate Financials Authenticate Fleet Manager | TC_003: Logout Financials >> TO_003 TC_003: Logout Fleet Manager >> TO_003 | /Tests/Financials/Home Page/Interaction/Value Entry Form/Authenticate Fleet Manager /Tests/Fleet Manager/Management and Information/Home Page/Interaction/Value Entry Form/Authenticate Fleet Manager | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-19
6 | MTC-FNC-0090 Add Special Service with Shipment in Finish status | Completed | Step 1: Financials page is displayed | Authenticate Financials | TC_002: Login with correct credentials >> TO_002 | /Tests/Financials/Home Page/Interaction/Value Entry Form/Authenticate Financials | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 2: Customer is selected | Financials Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_002 | /Tests/Financials/Home Page/Interaction/UI/Financials Home Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 3: Shipments page is displayed | Financials Home Page-UI Control Validation | TC_001: Controls of home page work >> TO_003 | /Tests/Financials/Home Page/Interaction/UI/Financials Home Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-21
|  |  | Step 4: Information is displayed | Search Buy Shipment Special Service Page-UI Control Validation | TC_001: Controls of Search Buy Shipment Special Service page work >> TO_001 | /Tests/Financials/Shipment Modifications/Interaction/UI/Search Buy Shipments Special Service Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 5: Result is displayed correctly | Search Buy Shipment Special Service Page-Search Shipment | TC_001: Search shipment with search criteria and Work Invoice created >> TO_001 | /Tests/Financials/Shipment Modifications/Funstions/Search Buy Shipments Special Service Page-Search Shipment | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 6: Shipment information is displayed | Search Buy Shipment Special Service Page-UI Links | TC_001: Links in Search Buy Shipment Special Service page work >> TO_001 | /Tests/Financials/Shipment Modifications/Interaction/UI/Search Buy Shipments Special Service Page-UI Links | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 7: OIC Pay Type changed. | Buy Shipment Special Service Page-UI Control Validation | TC_001: Control validation on special service page >> TO_001 >> TO_003 | /Tests/Financials/Shipment Modifications/Interaction/UI/Buy Shipment Special Service Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 8: Add Special Service module is displayed | Buy Shipment Special Service Page-UI Control Validation | TC_001: Control validation on special service page >> TO_002 | /Tests/Financials/Shipment Modifications/Interaction/UI/Buy Shipment Special Service Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 9: Special Service ID is selected | Buy Shipment Special Service Page-UI Control Validation | TC_001: Control validation on special service page >> TO_003 | /Tests/Financials/Shipment Modifications/Interaction/UI/Buy Shipment Special Service Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 10: Location is selected | Buy Shipment Special Service Page-UI Control Validation | TC_001: Control validation on special service page >> TO_003 | /Tests/Financials/Shipment Modifications/Interaction/UI/Buy Shipment Special Service Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 11: Information is displayed | Buy Shipment Special Service Page-UI Control Validation | TC_001: Control validation on special service page >> TO_004 | /Tests/Financials/Shipment Modifications/Interaction/UI/Buy Shipment Special Service Page-UI Control Validation | Completed | Completed |  |  |  | Huong Huynh | 2015-01-22
|  |  | Step 12: Service is added | Buy Shipment Special Service Page-Add Special Service | TC_001: Add special service to shipment >> TO_001 | /Tests/Financials/Shipment Modifications/Functional/Buy Shipment Special Service Page-Add Special Service | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-22
|  |  | Step 13: Correct message is displayed | Buy Shipment Special Service Page-Add Special Service | TC_001: Add special service to shipment >> TO_001 | /Tests/Financials/Shipment Modifications/Functional/Buy Shipment Special Service Page-Add Special Service | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-22
|  |  | Step 14: The Special Service is displayed in the shipment information in CCFM | Buy Shipment Special Service Page-Add Special Service | TC_001: Add special service to shipment >> TO_002 | /Tests/Financials/Shipment Modifications/Functional/Buy Shipment Special Service Page-Add Special Service | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-22
|  |  | Step 15: The OIC Pay Type is displayed in the shipment information in CCFM | Buy Shipment Special Service Page-Add Special Service | TC_001: Add special service to shipment >> TO_003 | /Tests/Financials/Shipment Modifications/Functional/Buy Shipment Special Service Page-Add Special Service | Completed | Completed |  |  |  | Giang Nguyen | 2015-01-22

## Customer Check
# | TM | Result on CERT
|  | 356900_Butterball | 482200_Butterball | 410400_Carrier | 500700_Louvl tile | 505500_Carlisle | 510700_Starbucks | 518700_Tempursealy | 518800_ST Feed | 521900_Halperns
1 | Assign, Force Assign And Unassign Driver to Shipment | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
2 | Authenticate CellComm | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
3 | Authenticate Financials | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
4 | Authenticate Fleet Manager | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
5 | Authenticate Master Schedules | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
6 | Authenticate MCP Report | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
7 | BatchUpdate Page-UI Links | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
8 | Buy Shipment Actions Page-UI Links | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
9 | Buy Shipment Finder Page-Search Shipment | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
10 | Buy Shipment Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
11 | Buy Shipment Result Page-UI Links | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
12 | Buy Shipment Special Service Page-Add Special Service | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
13 | Buy Shipment Special Service Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
14 | CellComm Home Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
15 | Create And Cancel Buy Shipment | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
16 | Create, Update, Copy, Deactivate and Delete Route | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
17 | Depart From Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
18 | Dispatch Page-Dispatch a Shipment | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
19 | Dispatch Page-Search Shipment | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
20 | Dispatch Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
21 | Dispatch Page-UI Elements | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
24 | Dispatch Page-UI Links | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
25 | Financials Home Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
26 | Fleet Manager Home Page-UI Links | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
27 | Master Schedules Home Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
28 | MCP Report Home Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
29 | Meal Break Page-Submit Meal Break | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
30 | Meal Break Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
31 | New Route Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
32 | New Route Page-UI Links | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
33 | Search Buy Shipments Special Service Page-Search Shipment | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
34 | Search Buy Shipments Special Service Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
35 | Search Buy Shipments Special Service Page-UI Links | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
36 | Search Shipments To Complete Page-Search Shipment | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
37 | Search Shipments To Complete Page-Set Shipment Complete | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
38 | Search Shipments To Complete Page-UI Control Validation | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS | PASS
1
0

## MCP Report_TM
Test Modules | 3
Test Cases | 6
MCP Report
Message
Functional
Interaction
UI
Test Module | Message Page-UI Control Validation | 0TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Test Case | TC_002:
Steps |  | Expected Result | Test Objective | Notes
4
5
6
VP
Value Entry Form
Management
Home Page
Functional
Interaction
UI
Test Module | MCP Report Home Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | Combo box works
TO_002 | Close button works
Pre-condition
1 | User is logged in MCP Report
Test Case | TC_001: Controls of home page work
Steps |  | Expected Result | Test Objective | Notes
1 | Select any customer in Select customer combo box
VP | Verify Select Customer combo box | The selected customer is displayed as the text of combo box Main page is displayed | TO_001
2 | Click Close (x) button
VP | Verify that MCP Report window is closed | MCP Report window is closed | TO_002
Value Entry Form
Test Module | Authenticate MCP Report | 3TC(s)
Test Objectives
TO_001 | Error message appears after login with incorrect credentials
TO_002 | Home Page appears after login with correct credentials
TO_003 | Logged Off page appears after logging off MCP Report
Test Case | TC_001: Login with incorrect credentials
Steps |  | Expected Result | Test Objective | Notes
1 | Navigate to MCP Report
2 | Login with incorrect user name and password
VP | Verify logging in with incorrect user name and password | Error message appears: "Invalid user name (entered user name) or password. Please try again" | TO_001
Test Case | TC_002: Login with correct credentials
Steps |  | Expected Result | Test Objective | Notes
3 | Login with correct user name and password
VP | Verify user login successfully | Home Page of MCP Report appears | TO_002
Test Case | TC_003: Logout MCP Report
Steps |  | Expected Result | Test Objective | Notes
4 | Click on Logoff link at the top right of Home Page
VP | Verify user logoff successfully | Message appears showing: "You are now logged off." | TO_003
Summary
Functional
Interaction
UI
Value Entry Form

## Master Schedules_TM
Test Modules | 7
Test Cases | 21
Master Schedules
Business Object
Route
Functional
Test Module |  | 1TC(s)
Test Objectives
Pre-Condition
Test Case | TC_001: Links work
Steps |  | Expected Result | Test Objective | Notes
Interaction
UI
Test Module | New Route Page-UI Links | 1TC(s)
Test Objectives
TO_001 | Edit link works
Pre-Condition
Test Case | TC_001: Links in New Route page work
Steps |  | Expected Result | Test Objective | Notes
1 | Log in to Master Schedule portal
2 | Select a customer
3 | Click on New Route.
4 | Fill all fields with a correct information
5 | Click on Add Stops button
6 | Click on Edit Link.
VP | Verify the link Edit works | A pop up window is diaplayed. | TO_001
Test Module | BatchUpdate Page-UI Links | 1TC(s)
Test Objectives
TO_001 | Page is displayed when clicking on page's link
Pre-Condition
1 | There are some active routes for a customer
Test Case | TC_001: Links work
Steps |  | Expected Result | Test Objective | Notes
1 | Log into Master Schedules portal
2 | Select a customer in pre-condition
3 | Select BatchUpdate tab
4 | Click on the page's links under the table that includes the route (ex: page 2, 3...)
VP | Verify the route is displayed | The route is displayed in the table | TO_001
Test Module | New Route Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | Correct values are displayed
TO_002 | Add Stops button works
TO_003 | Submit button works
TO_004 | Refresh Order Associations button works
TO_005 | Save Changes button works
TO_006 | Ok button works
Pre-Condition
Test Case | TC_001: Controls in New Route work
Steps |  | Expected Result | Test Objective | Notes
1 | Launch AUT
2 | Login with valid account
3 | Select Customer
4 | Go to New Route page
5 | Fill all fields with correct information
VP | Verify values at all fields | Correct values are displayed | TO_001
6 | Click on Add Stops button
VP | Verify the new row at Stop Detail table is displayed | Edit link, Sequence, Type, Site Code, Site Name,Action, Transit Days, Iterations, Req Match Days, Delete "x" and Add "+" icon are displayed | TO_002
7 | Click on Edit Link.
8 | Fill all fields with a correct information
VP | Verify values at all fields | Correct values are displayed | TO_001
9 | Click on Submit button.
VP | Verify data at Stop Detail table | The new data of the added stop is saved. | TO_003
10 | Click on Add Stop icon
11 | Click on Edit link.
12 | Fill out the fields with the correct information
13 | Click on Submit button.
14 | Click on Refresh Order Associations button then click on Orders tab.
VP | Verify data at Orders tab | The new order is displayed in the grid. | TO_004
15 | Click on Save Changes button.
VP | Observe the message | Confirmation message is displayed | TO_005
16 | Click on Ok button.
VP | Observe the message | Confirmation message is closed and another message is displayed: "Route <RouteName> has been created" | TO_006
Value Entry Forms
Test Module |  | 0TC(s)
Test Objectives
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
VP
LifeCycle
Test Module | Create, Update, Copy, Deactivate and Delete Route | 0TC(s)
Test Objectives
TO_001 | New route is created successfully
TO_002 | Information of route is modified successfully
TO_003 | New route is created successfully by copying from an existing route
TO_004 | Route is deleted by clicking on Delete link successfully
Pre-Condition
Test Case | TC_001: Creating Route works
Steps |  | Expected Result | Test Objective | Notes
1 | Log into Master Schedules portal
2 | Select a customer
3 | Select New Route tab
4 | Enter valid data into required fields
5 | Add 2 stops with valid data
6 | Click Refresh Order Associations
7 | Click Save Changes button
8 | Click OK button on Confirm dialog
VP | Verify notification message | Message displays to inform new route is created successfully | TO_001
Test Case | TC_002: Updating Route works
Steps |  | Expected Result | Test Objective | Notes
9 | Select Search/Modify Route tab
10 | Search the new created route
11 | Click on Modify link of the created route
12 | Click OK button on Confirm dialog
13 | Edit information of route
14 | Click Refresh Order Associations
15 | Click Save Changes button
16 | Click OK button on Confirm dialog
VP | Verify notification message | Message displays to inform route is modified successfully | TO_002
Test Case | TC_003: Copying Route works
Steps |  | Expected Result | Test Objective | Notes
17 | Click on Copy link of the modified route
18 | Enter name for the copy route
19 | Click Submit button on the dialog
20 | Search the new copied route
VP | Verify the copied route existed | The copied route is displayed in search result page | TO_003
Test Case | TC_004: Deleting Route works
Steps |  | Expected Result | Test Objective | Notes
21 | Search the route in pre-condition
22 | Click Delete link of the route
23 | Click OK button on Confirm dialog
VP | Verify notification message | Message displays to inform selected route is deleted | TO_004
Management
Home Page
Functional
Test Module |  | 2TC(s)
Test Objectives
TO_001
TO_002
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
VP
Test Case
Steps |  | Expected Result | Test Objective | Notes
3
VP
Interaction
UI
Test Module | Master Schedules Home Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | Selected customer is displayed after selecting
TO_002 | Functions tabs of Master Schedules page work
Pre-condition
1 | User is logged in Master Schedules
Test Case | TC_001: Controls of home page work
Steps |  | Expected Result | Test Objective | Notes
1 | Select any customer at Select Customer List
VP | Verify selected customer in the dropdown list | The selected customer is displayed as the text of dropdown list | TO_001
2 | Click on New Route tab
VP | Verify functions tabs of Master Schedules page work | Two different options are displayed and available (Shipment Details, Orders). | TO_002
3 | Click on BatchUpdate tab
VP | Verify functions tabs of Master Schedules page work | Route table is displayed | TO_002
Value Entry Forms
Test Module | Authenticate Master Schedules | 1TC(s)
Test Objectives
TO_001 | Error message appears after login with incorrect credentials
TO_002 | Home Page appears after login with correct credentials
TO_003 | Logged Off page appears after logging off Master Schedules
Test Case | TC_001: Login with incorrect credentials
Steps |  | Expected Result | Test Objective | Notes
1 | Navigate to Master Schedules Page
2 | Login with incorrect user name and password
VP | Verify logging in with incorrect user name and password | Error message appears: "Invalid user name (entered user name) or password. Please try again" | TO_001
Test Case | TC_002: Login with correct credentials
Steps |  | Expected Result | Test Objective | Notes
3 | Login with correct user name and password
VP | Verify user login successfully | Home Page of Master Schedules appears | TO_002
Test Case | TC_003: Logout Fleet Manager
Steps |  | Expected Result | Test Objective | Notes
4 | Click on Logoff link at the top right of Home Page
VP | Verify user logoff successfully | Message appears showing: "You are now logged off." | TO_003
Import
Functional
Test Module |  | 2TC(s)
Test Objectives
TO_001
TO_002
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
VP
Test Case
Steps |  | Expected Result | Test Objective | Notes
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
Pre-condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
Report
Functional
Test Module |  | 2TC(s)
Test Objectives
TO_001
TO_002
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
VP
Test Case
Steps |  | Expected Result | Test Objective | Notes
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
Pre-condition
Test Case
Steps |  | Expected Result | Test Objective | Notes

## Fleet Manager_TM
Test Modules | 22
Test Cases | 18
Fleet Manager
Business Object
Shipment
Functional
Test Module | Buy Shipment Finder Page-Search Shipment | 1TC(s)
Test Objectives
TO_001 | Shipments are displayed when searching from Buy Shipment by Shipment ID field
TO_002 | Shipments are displayed when searching from Assing Power Unit to Shipment by Shipment ID field
Pre-Condition
1 | There are some existed shipments
2 | Login Fleet Manager with valid account
Test Case | TC_001: Searching Shipment from Buy Shipment with valid data in Shipment tab
Steps |  | Expected Result | Test Objective | Notes
1 | Go to Shipment Management - Shipment Management - Buy Shipment
2 | In the Shipment ID field, type a valid shipment ID(e.g., 20130828-482700-SFTK_TEST_8/27)
3 | Select "Begin with"
4 | Click on Search button
VP | Verify search result grid | Shipments are displayed in the result's grid | TO_001
Interaction
UI
Test Module | Buy Shipment Result Page-UI Links | 1TC(s)
Test Objectives
TO_001 | Shipment details are displayed when clicking on Shipment ID link
Pre-Condition
1 | Login Fleet Manager with valid account
Test Case | TC_001: Links in Buy Shipment Result page work
Steps |  | Expected Result | Test Objective | Notes
1 | Go to Shipment Management - Shipment management - Buy Shipment
2 | Search any valid shipment
3 | Click on the Shipment ID
VP | Shipment details are displayed | Shipment details page are displayed | TO_001
Test Module | Buy Shipment Actions Page-UI Links | 1TC(s)
Test Objectives
TO_001 | Check Shipment (Create/Drop Process) link works
TO_002 | Check Shipment (Driver Assign Process) link works
TO_003 | Fleet Management > Assign > Driver link works
Pre-Condition
1 | Login to Fleet Manager
2 | Go to Fleet Management - Shipment Management - Shipment Management - Buy Shipments page, search for a shipment and select it
Test Case | TC_001: Links in Buy Shipment Actions page work
Steps |  | Expected Result | Test Objective | Notes
1 | Click on Actions button
2 | Click on Check Shipment (Create/Drop Process) link
VP | Verify Check Shipment (Create/Drop Process) link works | Process RE_PERFORM_SANITY_CHECK_SHIP_CREATED initiated window appears | TO_001
3 | Click on Check Shipment (Driver Assign Process) link
VP | Verify Check Shipment (Driver Assign Process) link works | Process RE_PERFORM_SANITY_CHECK_DR_ASSIGNED initiated window appears | TO_002
4 | Click on Fleet Management > Assign > Driver link
VP | Verify Fleet Management > Assign > Driver link works | Assign Driver to Shipment - Override Criteria window appears | TO_003
Test Module | Buy Shipment Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | All buttons work
Pre-Condition
1 | Login to Fleet Manager
2 | Go to Fleet Management - Shipment Management - Shipment Management - Buy Shipments page, search for a shipment and select it
Test Case | TC_001: Buttons in Buy Shipment page work
Steps |  | Expected Result | Test Objective | Notes
1 | Click on Status button
VP | Verify new window appears | Statuses pop up window is displayed | TO_001
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module | Create And Cancel Buy Shipment | 1TC(s)
Test Objectives
TO_001 | Shipment is created by running SO
TO_002 | System displayed message confirmation when canceling shipment without any assets assigned
TO_003 | Can't find the shipment after canceling shipment without any assets assigned
TO_004 | "No data was returned." message is displayed when searching a shipment
TO_005 | System displayed message confirmation when canceling shipment with all assets assigned
TO_006 | Can't find the shipment after canceling shipment with all assets assigned
Pre-Condition
1 | There is a newly created route |  |  | TC_001
2 | Have shipment without driver, power unit and equipment assigned. |  |  | TC_002
3 | Login to Fleet Management with valid account |  |  | TC_002
4 | Have shipment with driver, power unit and equipment assigned |  |  | TC_003
5 | Login to Fleet Management with valid account |  |  | TC_003
Test Case | TC_001: Create buy shipment by run SO
Steps |  | Expected Result | Test Objective | Notes
1 | Login to Master Schedules
2 | Select a customer
3 | Go to BatchUpdate tab
4 | Select SO From Date and SO To Date
5 | Check on the RUN SO checkbox of specific Route
6 | Click on Update & RunSO button
VP | Verify the status and Update & RunSO button | A confirmation message is displayed. (e.g., SO has been started). The Update & RunSO button is disabled | TO_001
7 | Click on Refresh button
VP | Verify the status and Update & RunSO button | The status is displayed as SUCCESS and Update & RunSO button is available | TO_001
8 | Login to MPC Report
9 | Select the same customer with Master Schedules
10 | Verify the message of created shipment | The status is displayed as Success and the shipment number is displayed in the Message text column. (e.g., OTM Order [20130828-482700-SFTK_TEST_8/27-001] created. [11882];Shipment [20130828-482700-SFTK_TEST_8/27] created (11883)). | TO_001
11 | Close MCP Report
12 | Login to Fleet Manager
13 | Go to Shipment Management - Shipment Management - Buy Shipments
14 | Enter the newly created shipment ID
15 | Click on Search button
16 | Verify the search result table | Shipment's results table is displayed with the information. | TO_001
Contact
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Driver
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Equipment
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Item
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Location
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Order Release
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Power Unit
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Tracking Event
Functional
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Pre-Condition
1
2
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Value Entry Form
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Lifecycle
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
TO_003
TO_004
TO_005
TO_006
Pre-Condition
1
2
3
4
5
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
5
6
VP
Business Transaction
Test Module | Assign, Force Assign And Unassign Driver to Shipment | 1TC(s)
Test Objectives
TO_001 | The Driver ID is displayed in the field after assigning Driver to Shipment successfully
Pre-Condition
1 | There are shipment and available drivers
2 | Login Fleet Manager with valid account
Test Case | TC_001: Assigning Driver to Shipment works
Steps |  | Expected Result | Test Objective | Notes
1 | Go to Shipment Management - Shipment Management - Buy Shipment
2 | In the Shipment ID field, type shipment ID at precondition
3 | Click on Search button
4 | Click on the Shipment ID
5 | Click on Actions button
6 | Click on Ok button from the confirmation message
7 | Enter to the assign Driver page through Fleet Management - Assign - Driver
8 | In the Assignment area, select the Manual ratio button and type the valid driver ID at pre condition
9 | Click on Ok button.
10 | Close pop-up window
11 | Go to Buy shipments search the shipment and then select the same shipment.
VP | Verify that the Driver ID field is populated with the driver ID | The Driver ID is displayed in the field | TO_001
Management and Information
Ask Oracle
Functional
Interaction
UI
Value Entry Form
Home Page
Functional
Test Module |  | 3TC(s)
Test Objectives
TO_001
TO_002
TO_003
Pre-Conditions
Test Case
Steps |  | Expected Result | Test Objective | Notes
Test Case
Steps |  | Expected Result | Test Objective | Notes
3
VP
Test Case
Steps |  | Expected Result | Test Objective | Notes
4
VP
Interaction
UI
Test Module | Fleet Manager Home Page-UI Links | 1TC(s)
Test Objectives
TO_001 | Buy Shipment Finder page is displayed after clicking on Shipment Management > Shipment Management > Buy Shipments link on the left menu
Pre-condition
1 | Navigate to Fleet Manager Page
2 | Login to with correct user name and password
Test Case | TC_001: Left menu links work
Steps |  | Expected Result | Test Objective | Notes
1 | Click on Management > Shipment Management > Buy Shipments link
VP | Verify link Shipment Management > Shipment Management > Buy Shipments works | Buy Shipment Finder page is displayed | TO_001
Value Entry Form
Test Module | Authenticate Fleet Manager | 3TC(s)
Test Objectives
TO_001 | Invalid user name (entered user name) or password. Please try again' message appears when logging in with incorrect username and password
TO_002 | Fleet Manager displays home page after logging in with correct credentials
TO_003 | Logged Off page appears after logging off Fleet Manager
Test Case | TC_001: Login with incorrect credentials
Steps |  | Expected Result | Test Objective | Notes
1 | Navigate to Fleet Manager Page
2 | Login with incorrect user name and password
VP | Verify logging in with incorrect user name and password | Invalid user name (entered user name) or password. Please try again' message appears | TO_001
Test Case | TC_002: Login with correct credentials
Steps |  | Expected Result | Test Objective | Notes
3 | Login with correct user name and password
VP | Verify user login successfully | Home Page of Fleet Manager appears | TO_002
Test Case | TC_003: Logout Fleet Manager
Steps |  | Expected Result | Test Objective | Notes
4 | Click on Logoff link at the top right of Home Page
VP | Verify user logoff successfully | Message appears showing: "You are now logged off." | TO_003
Container Optimization
Functional
Interaction
UI
Value Entry Form
Dispatch Board
Functional
Dispatch Board With Multi-Pane
Dispatch Board With Orders
Standard Dispatch Board
Test Module |  | 1TC(s)
Test Objectives
TO_001
Pre-Condition
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
4
VP
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
4
5
6
7
VP
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
4
5
6
7
VP
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
4
5
6
7
VP
Interaction
UI
Test Module |  | 1TC(s)
Test Objectives
TO_001
Test Case
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
4
5
6
7
VP
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
4
5
6
7
VP
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
4
5
6
7
VP
Test Module |  | 1TC(s)
Test Objectives
TO_001
TO_002
Test Case | TC_001:
Steps |  | Expected Result | Test Objective | Notes
1
2
3
VP
4
5
6
7
VP
Help
Interaction
UI
Location Asset Inventory
Functional
Interaction
UI
Value Entry Form
Logistics Guide
Functional
Interaction
UI
Value Entry Form

## Financials_TM
Test Modules | 10
Test Cases | 13
Financials
Billing
Functional
Interaction
UI
Value Entry Form
Shipment Modifications
Functional
Test Module | Search Shipments To Complete Page-Search Shipment | 1TC(s)
Test Objectives
TO_001 | Data are searched with shipment id
Pre-Condition
1 | User is logged in Financials
2 | Go to Shipment Modifications - Search Shipments To Complete page
Test Case | TC_001: Search criteria with shipment id
Steps |  | Expected Result | Test Objective | Notes
1 | Enter Shipment id to Search Criteria text box
2 | Click Search button
VP | Verify data can be searched correctly with shipment id | Correct data are displayed | TO_001
Test Module | Search Shipments To Complete Page-Set Shipment Complete | 1TC(s)
Test Objectives
TO_001 | Success message appears in Financials
TO_002 | Status of shipment is updated in Fleet Manager
TO_003 | Work invoice is created in Financials
Pre-Condition
1 | There is a shipment that is dispatched in CellComm
2 | User is logged in Financials
3 | Go to Shipment Modifications - Search Shipments To Complete page
Test Case | TC_001: Set shipment to complete
Steps |  | Expected Result | Test Objective | Notes
1 | Enter values to search shipments
2 | Click Search button
3 | Check on specific check box of Shipment to be set complete
4 | Click Set Ship Complete Yes button
VP | Verify success message appears | Message 'Changes Submitted' appears | TO_001
5 | Login to Fleet Manager
6 | Go to Shipment Management - Shipment Management - Buy Shipments page
7 | Search for the shipment which has set complete in Financials
8 | Open the shipment
9 | Click on Status button
VP | Verify the status of the shipment is updated | The shipment status for the SHIP_COMPLETE Type should be SHIP_COMPLETE_YES | TO_002
10 | Wait some minutes in order to verify the work invoice
11 | Go back to Financials
12 | Go to Shipment Modifications - Search Buy Shipment Special Service
13 | Enter shipment ID to Search Criteria text box
14 | Check on Work Invoice created radio button
15 | Click on Search button
VP | Verify work invoice is create for shipment | Completed shipment is displayed | TO_003
Test Module | Buy Shipment Special Service Page-Add Special Service | 1TC(s)
Test Objectives
TO_001 | Success message appears in Financials
TO_002 | The Special service is displayed in the shipment information in CCFM
TO_003 | The OIC Pay Type is displayed in the shipment information in CCFM
Pre-Condition
1 | User is logged in Financials
2 | Go to Shipment Modifications - Search Buy Shipment Special Service
Test Case | TC_001: Add special service to shipment
Steps |  | Expected Result | Test Objective | Notes
1 | Enter the Shipment number to search
2 | Click on 'Search' button
3 | Select a Shipment
4 | Select the checkbox OIC Pay type and change pay type from the list.
5 | Click on Add button
6 | Select a Special Service ID
7 | Select a Location
8 | Enter information in 'Quantity' field
9 | Click on 'Add Service'
10 | Click on "Submit Changes"
VP | Verify success message appears | The message "Shipment <..>:Requested Changes Submitted to ClearChain™ Fleet Manager. Please wait for a couple of minutes for the changes to reflect or to make any new changes to this shipment." appears | TO_001
11 | Login to Fleet Manager
12 | Go to Shipment Management - Shipment Management - Buy Shipments page
13 | Search for the shipment which is added special service in Financials
14 | Open the shipment
15 | Click on "Special Services" tab
VP | Observe the special services | Validate the special service is added in FN appears | TO_002
16 | Click on "Identification" tab
VP | Observe the "Reference Numbers" field | Validate that OIC Pay Type selected in step 4 appears | TO_003
Test Module | Search Buy Shipment Special Service Page-Search Shipment | 2TC(s)
Test Objectives
TO_001 | Data are searched with search criteria and Work Invoice created
TO_002 | Data are searched with search criteria and Shipment in Finish status
Pre-Condition
1 | User is logged in Financials
2 | Go to Shipment Modifications - Search Buy Shipment Special Service page
Test Case | TC_001: Search shipment with search criteria and Work Invoice created
Steps |  | Expected Result | Test Objective | Notes
1 | Enter values to Search Criteria text box
2 | Select Work Invoice created radio button
3 | Click Search button
VP | Verify data can be searched correctly with search criteria and Work Invoice created | Correct data are displayed | TO_001
Test Case | TC_002: Search shipment with search criteria and Shipment in Finish status
Steps |  | Expected Result | Test Objective | Notes
4 | Select Shipment in Finish status radio button
5 | Click Search button
VP | Verify data can be search correctly with search criteria and Shipment in Finish status | Correct data are displayed | TO_002
Interaction
UI
Test Module | Search Shipments To Complete Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | Search Criteria text box can be inputted data
TO_002 | Date time pickers From Date and To Date can be selected value
TO_003 | Check boxes can be checked and unchecked
Pre-Condition
1 | User is logged in Financials
2 | Go to Shipment Modifications - Search Shipments To Complete page
Test Case | TC_001: Controls of Search Shipments To Complete page work
Steps |  | Expected Result | Test Objective | Notes
1 | Enter values to Search Criteria text box
VP | Verify text box can be inputted data | Values are displayed correctly | TO_001
2 | Select any values for Date Time Pickers
VP | Verify all date time pickers From Date and To Date can be selected value successfully | The selected date is displayed as the text of text box | TO_002
3 | Click Search button
4 | Check/uncheck all check boxes in Shipment table
VP | Verify all check box can be checked/unchecked | All check boxes work correctly | TO_003
Test Module | Search Buy Shipment Special Service Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | Search Criteria text box can be inputted data
TO_002 | Radio buttons can be selected
Pre-Condition
1 | User is logged in Financials
2 | Go to Shipment Modifications - Search Buy Shipment Special Service page
Test Case | TC_001: Controls of Search Buy Shipment Special Service page work
Steps |  | Expected Result | Test Objective | Notes
1 | Enter values to Search Criteria text box
VP | Verify text box can be inputted data | Values are displayed correctly | TO_001
2 | Select all radio buttons
VP | Verify all radio buttons can be selected | All radio buttons work correctly | TO_002
Test Module | Search Buy Shipment Special Service Page-UI Links | 1TC(s)
Test Objectives
TO_001 | Buy Shipment Special Service details are displayed when clicking on Shipment ID link
Pre-Condition
1 | User is logged in Financials
2 | There are some shipments in the grid after searching
Test Case | TC_001: Links in Search Buy Shipment Special Service page work
Steps |  | Expected Result | Test Objective | Notes
1 | Click on the Shipment ID link
VP | Verify Shipment ID link works | Shipment information is displayed in Buy Shipment Special Service page | TO_001
Test Module | Buy Shipment Special Service Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | Validating check boxes
TO_002 | Validating buttons
TO_003 | Validating combo boxes
TO_004 | Validating text boxes
Pre-Condition
1 | User is logged in Financials
2 | Go to Shipment Modifications - Search Buy Shipment Special Service page
3 | Search for a shipment and select it
Test Case | TC_001: Control validation on special service page
Steps |  | Expected Result | Test Objective | Notes
1 | Checked and Unchecked the OIC Pay Type
VP | Verify checked and unchecked the oic pay type | The checkbox OIC Pay Type is checked/unchecked | TO_001
2 | Change pay type from the list. Ex: TEAM
VP | Verify changing pay type | "TEAM" pay type is displayed as text of OIC Pay Type combo box | TO_003
3 | Click on Add button
VP | Verify Add Special Service area is displayed | Add Special Service area is displayed with following items: - Shipment ID - Special Service ID - Actual Distance - Spl Srv ID Address - Location - Quantity - Actual Duration - Actual Date/Time | TO_002
4 | Select a Special Service ID
VP | Verify selecting Special Service ID | The Special Service ID is selected | TO_003
5 | Select a Location
VP | Verify selecting a location | The Location is selected | TO_003
6 | Enter data in 'Quantity' field
VP | Verify entering data in quantity field | The data is remained in the quantity field | TO_004
Value Entry Form
Payroll
Functional
Interaction
UI
Value Entry Form
Home Page
Functional
Interaction
UI
Test Module | Financials Home Page-UI Control Validation | 1TC(s)
Test Objectives
TO_001 | Selected customer is displayed after selecting one customer
TO_002 | Search shipment to complete page is displayed after selecting "Search Shipment to complete "menu link
TO_003 | Search buy shipment special service page is displayed after selecting "Search buy shipment special service" menu link
Pre-Condition
1 | User is logged in Financials
Test Case | TC_001: Controls of home page work
Steps |  | Expected Result | Test Objective | Notes
1 | Select any customer in Select customer combo box
VP | Verify selected customer in the dropdown list | The selected customer is displayed as the text of combo box | TO_001
2 | Navigate to Shipment Modifications>Search shipment to complete
VP | Verify page is displayed correctly | Search shipment to complete page is displayed | TO_002
2 | Navigate to Shipment Modifications>Search buy shipment special service
VP | Verify page is displayed correctly | Search buy shipment special service page is displayed | TO_003
Value Entry Form
Test Module | Authenticate Financials | 3TC(s)
Test Objectives
TO_001 | Invalid user name (entered user name) or password. Please try again' message appears when logging in with incorrect username and password
TO_002 | Financials displays home page after logging in with correct credentials
TO_003 | Logged Off page appears after logging off Financials
Test Case | TC_001: Login with incorrect credentials
Steps |  | Expected Result | Test Objective | Notes
1 | Navigate to Financials Page
2 | Login with incorrect user name and password
VP | Verify logging in with incorrect user name and password | Invalid user name (entered user name) or password. Please try again' message appears | TO_001
Test Case | TC_002: Login with correct credentials
Steps |  | Expected Result | Test Objective | Notes
3 | Login with correct user name and password
VP | Verify user login successfully | Home Page of Financials appears | TO_002
Test Case | TC_003: Logout Financials
Steps |  | Expected Result | Test Objective | Notes
4 | Click on Logoff link at the top right of Home Page
VP | Verify user logoff successfully | Message appears showing: "You are now logged off." | TO_003

## CellComm_TM
Test Modules | 11
Test Cases | 24
CellComm
Business Object
Driver
Functional
Interaction
UI
Value Entry Forms
LifeCycle
Management and Information
Configuration
Functional
Interaction
UI
Home Page
Functional
Interaction
UI
Test Module | CellComm Home Page-UI Control Validation | 6TC(s)
Test Case | TC_001: All tabs in Home page works
Test Objectives
TO_001 | Dispatch page is displayed when clicking on Dispatch tab
Steps |  | Expected Result | Test Objective | Notes
1 | Login to CellComm with a valid credential
2 | Click on Dispatch tab
VP | Verify the Dispatch page is displayed | The Dispatch page is displayed | TO_001
Test Case | TC_002: Data are displayed correctly when clicking on links
Test Objectives
TO_002 | Data are displayed correctly under location link
TO_003 | Data are displayed correctly under language link
Steps |  | Expected Result | Test Objective | Notes
3 | Click location link at the top right
VP | Verify data are displayed under the link | Correct data are displayed | TO_002
4 | Click language link at the top right
VP | Verify data are displayed under the link | Correct data are displayed | TO_003
Test Module | CellComm Home Page-UI Elements | 1TC(s)
Test Case | TC_001: Home page is displayed correctly
Test Objectives
TO_001 | UI elements in Home page are displayed
Steps |  | Expected Result | Test Objective | Notes
1 | Login to CellComm
VP | Verify UI elements in Home page | The following fields are displayed: - Label: Welcome, <username> - Link: Help, Contact, Logoff, Change, location, language, Privacy Policy, Terms and Conditions, Disclaimer - Textbox: Search - Button: Search | TO_001
Value Entry Form
Test Module | Authenticate CellComm | 3TC(s)
Test Objectives
TO_001 | Error message appears when login with incorrect credentials
TO_002 | Home Page appears when login with correct credentials
TO_003 | Logged Off page appears when logoff CellComm
Test Case | TC_001: Login with incorrect credentials
Steps |  | Expected Result | Test Objective | Notes
1 | Navigate to CellComm Page
2 | Login with 3 scenarios: + incorrect user name and incorrect password + incorrect user name and correct password + correct user name and incorrect password
VP | Verify error message | Error message appears showing: "Incorrect User ID or Password" | TO_001
Test Case | TC_002: Login with correct credentials
Steps |  | Expected Result | Test Objective | Notes
3 | Login with correct user name and password
VP | Verify user can login successfully | Home Page of CellComm appears | TO_002
Test Case | TC_003: Logout CellComm
Steps |  | Expected Result | Test Objective | Notes
4 | Click on Logoff link at the top right of Home Page | User is logoff successfully
VP | Verify user can logout successfully | Message appears showing: "Your session has been terminated. For added security, please close your browser." | TO_003
Phone Map
Functional
Interaction
Shipment
Functional
Test Module | Dispatch Page-Search Shipment | 3TC(s)
Test Case | TC_001: Searching shipment by Date and Route
Test Objectives
TO_001 | Searching shipment works by valid Date and Route
Pre-Condition | The driver has shipment assigned
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Navigate to Dispatch tab
4 | Select valid date
5 | Select Route in Shipment combo box
6 | Click Get Shipment button
VP | Verify searching shipment | 1. The correct Shipment Name is displayed above the table 2. The number of stops is correct 3. The Tractor is correct 4. The Driver ID is correct | TO_001
Test Case | TC_002: Searching shipment by Shipment name
Test Objectives
TO_002 | Searching shipment works by valid Shipment name
Pre-Condition | All search data is cleared
Steps |  | Expected Result | Test Objective | Notes
7 | Enter a valid shipment with case sensitive in Shipment Name textbox (e.g 20141028-425400-999sfttkvk)
8 | Click Get Shipment button
VP | Verify searching shipment | 1. The correct Shipment Name is displayed above the table 2. The number of stops is correct 3. The Tractor is correct 4. The Driver ID is correct | TO_002
Test Case | TC_003: Searching shipment by all data
Test Objectives
TO_003 | Searching shipment works by all valid data
Pre-Condition | All search data is cleared
Steps |  | Expected Result | Test Objective | Notes
9 | Enter a valid shipment in Shipment Name textbox
10 | Select valid date
11 | Select Route in Shipment combo box
12 | Click Get Shipment button
VP | Verify searching shipment | 1. The correct Shipment Name is displayed above the table 2. The number of stops is correct 3. The Tractor is correct 4. The Driver ID is correct | TO_003
Test Module | Dispatch Page-Dispatch a Shipment | 2TC(s)
Test Case | TC_001: Arriving a stop
Test Objectives
TO_001 | Arriving first stop
Pre-Condition | The shipment has been assigned driver
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Navigate to Dispatch tab
4 | Search shipment in Pre-condition
5 | Click on Arrive link
6 | Enter valid Trailer, Tractor and departure date/time
7 | Click on Submit button
VP | Verify submitting departure form | 1. Arrival Form is closed 2. The typed Arrival Date/Time is displayed in the column 3. The Depart link should be displayed 4. The Timezone should be the same that shipment 5. Arrival date should be greater than estimated | TO_001
Test Case | TC_002: Departing a stop
Test Objectives
TO_002 | Departing first stop
TO_003 | The "Fuel Stop", "Meal Break", "Layover", "Rest Break" and "Break Down" buttons display correctly
Pre-Condition | The shipment has been arrived at a stop
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Navigate to Dispatch tab
4 | Search shipment in Pre-condition
5 | Click on Depart link
6 | Fill out the mandatory fields. Hub Miles: (e.g., 10). Fuel Level: (e.g., 8). Trailer: (e.g., ######). Tractor: (e.g., ######). Departure: (e.g., Same as scheduled). BOL: (e.g., optional). Weight: (e.g., optional). Pieces: (e.g., optional). Late arrival Code: (e.g., optional). Late Departure Code: (e.g., optional). Meal brak time: (e.g., optional). Delivery Exception: (e.g., optional). Spotting: (e.g., optional). Drop Hook: (e.g., optional).
7 | Click on Submit button
VP | Verify submitting departure form | 1. Departure window is closed 2. The Departure Date/Time is displayed in the column of the stop. 3. Arrive link is displayed in the follow stop on the Action column. | TO_002
VP | Validate the "Fuel Stop", "Meal Break", "Layover", "Rest Break" and "Break Down" buttons are displayed | The buttons is displayed correctly | TO_003
Test Case | TC_003: Arrive and Depart other stops
Test Objectives
TO_004 | Arrive and Depart all stops
Steps |  | Expected Result | Test Objective | Notes
8 | Arrive all remaining stops
9 | Depart all remaining stops
VP | Verify stops after departed | All stops are completed. | TO_004
Test Case | TC_004: Shipment status after dispatched
Test Objectives
TO_005 | Shipment status displays as SHIP_FINISHED_YES
Steps |  | Expected Result | Test Objective | Notes
9 | Submit meal break
10 | Navigate to CCFM
11 | Search shipment in Pre-condition
12 | Click on the shipment
13 | Click on Status button
VP | Verify the status of the shipment | In the status value column, the shipment status is displayed correctly as SHIP_FINISHED_YES | TO_005
Test Module | Meal Break Page-Submit Meal Break | 1TC(s)
Test Case | TC_001: Submit meal break
Test Objectives
TO_001 | Meal Break is submitted successfully
Pre-condition | 1. There is an active shipment which has first stop is arrived/departed
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Click Dispatch tab
4 | Search shipment in Pre-condition
5 | Click on Meal Break button
6 | Fill out the following fields: Hub Miles: (e.g., 100) Arrival Date/Time (e.g., Actual date + 12:00:00) Departure Date/Time (e.g. Actual date + 12:30:00) Time Zone: (e.g., EST5EDT) Street: (e.g: 3000 Auburn Dr) City: (e.g., Beachwood) State: (e.g., OH)
7 | Click on Submit Query button
VP | Verify behaviour | 1. Pop up window is closed. 2. New NFR stop is added | TO_001
Interaction
UI
Test Module | Dispatch Page-UI Elements | 2TC(s)
Test Case | TC_001: UI Elements of Dispatch Page display
Test Objectives
TO_001 | Dispatch Page's elements are displayed
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Navigate to Dispatch tab
VP | Verify Dispatch Page's elements display on screen | Elements are displayed on Dispatch page include: 1. Dispatch label 2. Search Shipment label 3. Shipment Name label + textbox 4. Date label + textbox + calendar icon 5. Shipment label + combo box 6. Get Shipment button | TO_001
Test Case | TC_002: UI Elements of Search grid display
Test Objectives
TO_002 | Elements of search grid display after searching shipment
Steps |  | Expected Result | Test Objective | Notes
4 | Enter a valid shipment name
5 | Click on Get Shipment button
VP | Verify elements in search grid display on screen | In the first stop the link 'Arrive" should be displayed in the action column. | TO_002
Test Module | Dispatch Page-UI Control Validation | 3TC(s)
Test Case | TC_001: Error message displays in correct colour
Test Objectives
TO_001 | Error message displays in red
Pre-condition | 1. There is an active location 2. There is an active shipment belongs to the location
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Click Dispatch tab
4 | Click submit button without any input
VP | Verify the displayed error message | The field is displayed in red colour. | TO_001
Test Case | TC_002: Combo box works
Test Objectives
TO_002 | Correct options are displayed in combo box
Steps |  | Expected Result | Test Objective | Notes
5 | Select a valid date
VP | Verify the route in Shipment combo box | The route option(s) displays in the list | TO_002
Test Case | TC_003: Button works
Test Objectives
TO_003 | Clicking on buttons display correct popup/window
Steps |  | Expected Result | Test Objective | Notes
6 | Search shipment in Pre-condition
7 | Arrive and Depart the first stop
8 | Click on Meal Break button
VP | Verify popup window displays | A meal break pop up window is displayed | TO_003
Test Module | Dispatch Page-UI Links | 1TC(s)
Test Case | TC_001: Arrive and Depart links work
Test Objectives
TO_001 | Arrival Form displays when clicking on Arrive link
TO_002 | Departure Form displays when clicking on Depart link
Pre-condition | 1. There is an active location 2. There is an active shipment belongs to the location
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Navigate to Dispatch tab
4 | Click on Arrive link under Action column
VP | Verify Arrive link | The Arrival Form is displayed | TO_001
5 | Enter Arrival information and click Submit Query button
6 | Click on Depart link
VP | Verify Depart link | The Departure Form is displayed | TO_002
Test Module | Meal Break Page-UI Control Validation | 1TC(s)
Test Case | TC_001: Proper data displays after input
Test Objectives
TO_001 | Data displays correctly after inputting in textbox
Pre-condition | 1. There is an active shipment which has first stop is arrived/departed
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Click Dispatch tab
4 | Search shipment in Pre-condition
5 | Click on Meal Break button
6 | Fill out the following fields: Hub Miles: (e.g., 100) Arrival Date/Time (e.g., Actual date + 12:00:00) Departure Date/Time (e.g. Actual date + 12:30:00) Time Zone: (e.g., EST5EDT) Street: (e.g: 3000 Auburn Dr) City: (e.g., Beachwood) State: (e.g., OH)
VP | Verify the input info | All information is displayed | TO_001
Test Case | TC_002: Button works
Test Objectives
TO_002 | Buttons on Meal Break page works correctly
Steps |  | Expected Result | Test Objective | Notes
7 | Click on Submit Query button
VP | Verify behaviour | 1. Pop up window is closed. 2. New NFR stop is added | TO_002
Value Entry Form
Test Module | Depart From Validation | 2TC(s)
Test Objectives
TO_001 | "Error: Enter Valid Search Criteria" message displays when submitting form with no data
TO_002 | "Error: Invalid Date" message displays when erasing Date field
TO_003 | "Error: Enter Valid Search Criteria" message displays when submitting form with blank Shipment combo box
Test Case | TC_001: Error message displays when submitting form with missing data
Steps |  | Expected Result | Test Objective | Notes
1 | Login CellComm Page
2 | Select location
3 | Navigate to Dispatch tab
4 | Click on Get Shipment button without any input
VP | Verify the behaviour | Error message is displayed beside Route name field (e.g., Error: Enter Valid Search Criteria). | TO_001
Test Case | TC_002: Error message displays when input invalid data
Steps |  | Expected Result | Test Objective | Notes
5 | Delete the information on Date field
VP | Verify the behaviour | An error message is displayed "Error: Invalid Date" | TO_002
6 | Select "blank" option in Shipment field
7 | Click on Get shipment button
VP | Verify the behaviour | An error message is displayed "Error: Enter Valid Search Criteria" | TO_003